## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Resume Analysis / Resume Building Analysis
PROJECT SPONSER | Tushar Topale
PROJECT MANAGER
EXPECTED START DATE | 2023-08-01
EXPECTED COMPLETION DATE | 2023-08-30
ESTIMATED COST | 0
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of the project is to conduct a Comprehensive Analysis of students to gain insights about relationship between their Academic Performance, Event Participation, Career Aspiration and other factors influencing their success.
BUSINESS CASE | To help millons of students to get insights about relationship between students economic background, academic performance, competence, expected salary in a cost effective way.
GOALS/METRICS | To create a Dashboard/Report based on aspects like student's academic performance,event participation, career aspiration, and other features within the estimated deadlineusing resources like Data Visualization tools and other references.
EXPECTED DELIVERABLES | A demo video of our visualizations (Dashboard), code(.pbix and github link), and project documentation (project charter, SRS, WBS, project plan, Raid logs, Lessons learnt, project report).
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | 1. Analysing the data, transforming the data, loading Data. 2.Choosing the Visual( graphs, Tables/matrix. 3.Providing a Dashboard/Report.
OUTSIDE OF SCOPE | Providing Triggers/Warnings/Notifications, Access to Dashboard for the user/Student.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Harshita Kilari
SUPPORT RESOURCES | Microsoft Power BI tool Special needs: Python libraries( Numpy, Pandas, Matplotlib)
COST ALLOCATION | Project budget=0
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Harshada Topale
KEY STAKEHOLDERS | Harshada Topale
END CUSTOMERS | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | The process of Data Cleaning should be done right( like the format of the column "Family Income" is in text form we have to carefully turn it into number format ) else the whole procedure turns wrong and this effects the project.
ASSUMPTIONS | Assuming that all the filters in "Designation" column in data as students/interns while answering questions.
CONTRAINTS | No constriants so far.
MILESTONES
REQUIREMENT GATHERING | 2023-08-04
PLANNING | 2023-08-08
DESIGN | 2023-08-12
DEVELOPMENT | 2023-08-22
TESTING | 2023-08-25
DEPLOYMENT | 2023-09-25
CLOSURE | 2023-09-28