## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## project plan
PROJECT PLAN
INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Resume Analysis
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Resume building insights , project report
PROJECT SCOPE
PROJECT START DATE | 2023-08-01
PROJECT END DATE | 2023-08-30
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | REQUIRED TIME( IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation
1.1 | Identify business problem | 3hrs | 2023-08-01 | 2023-08-01 | 1 | COMPLETED
1.2 | Create a project charter | 2hrs | 2023-08-02 | 2023-08-02 | 1 | COMPLETED
1.3 | Create SRS document |  | 2023-08-03 | 2023-08-03 | 1 | COMPLETED
1.4 | Requirement gathering | 2hrs | 2023-08-03 | 2023-08-04 | 1 | COMPLETED
| Requirement Elicitaion meeting | 2hrs | 2023-08-05 | 2023-08-05 | 1 | COMPLETED
2 | Planning
2.1 | Deciding technology to be used | 1hr | 2023-07-06 | 2023-08-06 | 1 | COMPLETED
2.2 | Create Work breakdown structure (WBS) | 1hr | 2023-08-07 | 2023-08-07 | 1 | COMPLETED
2.3 | Create Project plan | 1hr | 2023-08-07 | 2023-07-07 | 1 | COMPLETED
2.4 | Create RAID log | 2hrs | 2023-08-08 | 2023-08-09 | 2 | COMPLETED
3 | Execution
3.1 | Design stage
Data Cleaning
3.1.1 | Excel
| Checking for null values | 1hr | 2023-09-08 | 2023-09-08 | 1 | COMPLETED
| created a new column named "Event details" | 1hr | 2023-10-08 | 2023-10-08 | 1 | COMPLETED
3.1.2 | Power BI
| removing duplicates with respect to column "Email id" | 1hr | 2023-11-08 | 2023-11-08 | 1 | COMPLETED
3.1.2.1 | Conditional Column
| created a new column named "Average Family Income" based on Family Income | 2hrs | 2023-12-08 | 2023-12-08 | 1 | COMPLETED
3.1.2.2 | Loading Data
| successfully applied all the changes and loaded data table into power BI | 1hr | 2023-12-08 | 2023-12-08 | 1 | COMPLETED
3.2 | Development stage
Data Modeling
3.2.1 | Answering simple questions
| Creating Measures, Visualisations for each question | 5hrs | 13/08/2023 | 15/08/2023 | 3 | COMPLETED
3.2.2 | Answering Moderate questions
| Creating Measures, Visualisations for each question | 6hrs | 16/08/2023 | 22/08/2023 | 5 | COMPLETED
3.3 | Testing stage
Dashboarding
3.3.1 | Created a visualisation report for students to view the relation between the key attributes. | 3hrs | 24/08/2023 | 25/08/2023 | 2 | COMPLETED
3.4 | Deployment stage
3.4.1 | Lesson's Learnt log | 4hrs | 23/09/2023 | 24/09/2023 | 2 | COMPLETED
3.4.2 | Project Report | 10hrs | 25/09/2023 | 28/08/2023 | 4 | COMPLETED
3.5 | Project Closure | 1hr | 28/09/2023 | 28/09/2023 | 1 | COMPLETED